## Sheet1
Department | S. No | Risk Category | Risk Owner | Risk Description |  |  |  | Risk Treatment
|  |  |  | Description | Inherent Risk Level (Impact/ Likelihood) | Current Mitigation | Current Risk Level (Impact/ Likelihood) | Action owner | Action Plan | Targeted Date
FIN | 1 | Budget palnning and management | Jayesh | Incorrect Assumptions/ Forecasts (RC) for Annual Budget & Plan (RE) resulting inappropriate planning (C ) | 3D | Expenses monitored quarterly against Budget , SUG Price and exchange rates are assumed based on available long term projections; (Mitigation measure is for budget control post allocation of Budget) Unforeseen increase in the above and other components is being reviewed by Senior Management/ Board. Any increase in costs is covered as per agreement. | 2C | Suchibrata
FIN | 2 | GTA Invoice processing | ramesh | Delay in raising of GTA Invoices (RC) and its delayed collection (C)impacting working capital (RE ) | 4E | Fortnightly GTA invoices are raised on 1st working day from the end of FN and are collected within 4 working days; Incase of delay in collection CCM team / Budget Planning and Billing team levies Interest as per agreement terms | 2C | Seema
FIN | 3 | Credit Management | priya | Inadequate financial security due to weak credit control process (RC) diffculty in recovery (RE) resulting in default (C ) | 5C | Ensures payment security for all customers (except RIL and GSPL- Gujarat State Petronet Limited) before initiating gas transportation or enhancing Maximum Delivery Quantity (MDQ), either through (a) Letter of Credit or (b) Security Deposit or (c) advance payment. On Quarterly basis, Lead CCM monitors customer credit and ensures gas transportation is not allowed in case customer outstanding is more than 80% of the maximum-security available at all times. Online Credit monitoring portal developed for monitoring of credit line on real time basis | 4E | Seema
FIN | 4 | Vendor Payment Management | raj | Payments recorded are invalid, inaccurate (RC), and posted in inappropriate period/ wrong vendor (RE) resulting incorrect financials/ vendor balances/ fradulent payment (C). | 2B | Treasury team executes payment proposal, created by AP team, in SAP which automatically raises payment requests on the bank portal (host to host) and the authorized signatory approves payment request on bank portal using authorized bank ids & SAP is configured to auto-record the payment journal entry. In exceptional cases, manual payments are processed after approval by the authorized signatories;Monthly BRS is done to ensure booking are done in appropriate period | 3C | Subhransu
FIN | 5 | User Access management of system | priya | Unauthorized and inappropriate user access (RC) may results in fraudulent (RE) and incorrect accounting (C ). | 2B | SAP IT Team will provide the access control matrix of Finance module to Respective Functional Heads, Employees' access to SAP are reviewed on annual basis by the Respective Functional Heads and validated by CFO to ensure that there are proper access restriction and segregation of duties. Access to the various System SAP modules is appropriately restricted, and Inactive or unauthorized users and roles are removed promptly by SAP IT Team based on notification by e-mail/termination information received from HR team. | 3C | Priti
FIN | 6 | Inventory management | raj | Inventory appearing in the SAP do not exist physically (RC) resulting in misstatement of closing stock (RE) & incorrect financials (C ). | 2E | Physical verification for inventory is carried out by authorized personnel from the Stores Department as well as a third party. -Discrepancies in physical verification without financial impact are reviewed & approved by Site Discipline Lead, Area Manager, Head of department of Concerned function and Head of Department materials, and VP - Accounts & Audit; -Discrepancies having a financial impact are reviewed and approved by the CFO and MD.Internal Auditor (external) will also check inventory once in three years on test check basis. | 1A | Malay
FIN | 7 | investment/redemption in Mutual funds | Jayesh | Unauthorized (RC) Mutual Fund (MF) purchase or sale (RE) resulting in fraudulent transactons (C ) | 5E | Treasury team analyses the cash flow position and invests in mutual funds based on the Treasury policy approved by Board. Treasury Head reviews the assessment of the Treasury team and approves the investment/redemption in Mutual funds. Based on the approval, the treasury team executes the transaction. All MF folios are linked with company bank accounts so redemption happens automatically in company accounts. | 4E | Seema
FIN | 8 | PO approval as per DOA | jatin | POs not approved as per Delegation of Authority (DoA) (RC) leading to excess procurement or procurement of substandard materials/services (RE) at a higher rate (C). | 3D | - Framework Order - SAP is configured to restrict the creation of framework order exceeding the Annual rate contract value; - Purchase Order - SAP is configured to de-list the PO if any line item in the PO is greater than 200% of the PR value; - Framework order and Annual rate contracts are created in SAP when the rates are pre-fixed with the vendors, but the quantities are determined later based on requirements; - SAP has automated control for tracking the PO’s created against each PR item number. Single PR may have multiple PO in case of multiple vendors selected for different states etc.; - PO gets released as per released strategy defined in SAP as per DOA . | 3D | Pradeep Rawat
FIN | 9 | Vendor management | snil | Creation of Fictitious Vendor (RC/ RE) resuting in fraudulent payment (C) | 4E | System of Vendor master creation in place ensuring maker checker in place Periodic Review of Vendor master | 4C | Subhransu
FIN | 10 | Bank accounts or banking signatories (RC) | sunil | Unauthorized bank accounts or banking signatories (RC) may result in invalid / fraudulent transactions (RE) | 4E | Treasury Head provides bank with approved board resolutions for opening/closing of bank accounts including updates to banking signatories for existing accounts. | 4C | Seema
FIN | 11 | Management of Asset Register | sunil | Assets appearing in the FAR do not exist physically (RC) resulting in misstatement of Fixed Assets (RE) | 4E | PV of Fixed Assets is conducted on a rotational basis to cover all Fixed Assets once in three years. Respective Area Location Managers / IT Team do a fixed asset physical verification, and independent accounts personnel reviews the reconciliations and resolve all discrepancies above threshold limit of INR 50,000 (WDV value) per asset code. Fixed Assets PV report is reviewed by Head Field O&M (Operation & Maintenance) / Head IT/Admin Head, Vice President - Accounts & Audit. CFO / CEO approval to be obtained for posting any adjustment (shortage,etc) entries in SAP. | 4C | Subhransu
FIN | 12 | Site Imprest | jasmin | Site imprest expenses are unauthorised or in excess of limits | 5B | Imprest Policy mentions allowable expensed and approvals/ limits for each category of expense. Review and approval of exceptional site expenses happens as defined in Sub DOA. AP team processes the imprest based on the approvals. | 1D | Subhransu
FIN | 13 | Financial statement & Disclosure | jasmin | Misstatement in the financial statements & disclosures | 5B | Financial statements are prepared by member of accounts team on a quarterly basis and are reviewed by VP Accounts & Audit and subsequently reviewed by the statutory auditors. | 1D | Nupur
FIN | 14 | Tax Compliance | Bholu | Tax compliances including annual returns | 5B | Tax team prepares the computation and returns & tax compliances on a monthly/ quarterly/ annual basis and is reviewed by Chief General Manager- Taxation. | 1D | Kunal
FIN | 15 | Financial/ restrictive covenants management and periodic reporting | Bholu | Failure to comply with the financial/ restrictive covenants or periodic reporting may result in declaration of event of default triggering mandatory redemption /imposition of penal interest rate / invocation of security under financial arrangement | 1D | -PUA with Reliance providing certainty of cash flow. -The periodic monitoring of covenants is duly mapped on the NSDL DLT Portal -Applicable compliance reports are communicated to the Debenture Trustee and are also hosted on the Company’s website -Certification by Statutory auditors on financial covenants on quarterly basis -Debt servicing is done prior to distribution to unit holders | 1D | Seema/Nupur
FIN | 16 | Related party transactions | seema | Related party transactions resulting from InvIT framework agreement, Investment management agreement, NCD issued by PIL and any such transaction in ordinary course of business may involve Conflict of Interest | 1D | -Arm’s Length analysis of transections from third party -Board/Audit Committee approval for significant RPTs and quarterly review by audit committee -Detailed reporting in financial statements and regulatory filings to maintain stakeholder trust | 1D | Nupur
HR | 17 | Recruitment & Hiring | Shruti N. | Delay in acquisition of key Positions leading to operational disruption and strategic setbacks | 3D | 1. Tie-ups with reputed recruitment agencies that can help quickly identify and secure qualified candiates 2. Internal Job Posting (IJPs) and sourcing through internal referrals 3. Successors identified and developed - immediate and in subsequent time frames as per Succession plan | 2C | Jayesh | new plan 1 | 2026-07-28
|  |  | Manali | Inadequate background checks | 3C | 1. Continuous review of BGV's for each cases 2. Internal audit of BGV reports to track and monitor effective and timely closure of background checks | 2C | ramesh | new plan 2
|  |  | Manali | Attrition risk : Inability to retain people at key positions | 3D | 1. Retention planning for key talent, critical positions 2. Identification and development of young emerging leaders to take up leadership positions in future 3.Incentives linked to performance ; Larger roles and opportunities 4. Successors identified - immediate, and in subsequent time frames as per Succession plan 5. Wellbeing driven initiatives | 3C | Jayesh | new plan 3 | 2026-07-28
HR | 18 | Employee Exp. | Abhijit S. | Employee Disengagement and Inadequate talent Development impacting performance and business objectives | 2C | 1. SMART goals based Performance Management 2. Mid year and annual performance review process 3. Engagement through communication chanels like Listen-hours, Townhalls, suggestion box 4. Driving meaningful engagement initiatives 5. Leadership and High potential emloyees development program 6. Calendarized functional, technical and behavioral trainings for employees are in place 7. E-learnings and Self paced learnings 8 Coaching 9. Wellbeing Initiatives | 2B
HR | 19 | Complaiance Mgt. | Manali | Non-compliance to applicble labour laws leading to Penalities, fines, prosecution etc. | 3D | 1. All applicable labour compliances are mapped on Compliance tools 2. Updates and new compliances are incorporated as received from external Third party (PWC / Transient). 3. Compliance submission is outsourced to third party specialised in Labour compliance (Transient) 4. Review of submissions through layered mechanism depending on criticality of compliance. 5. Non-compliances are highlighted in Various MIS and Exception reports along with remediations and designated owner. | 3C | aditya | plan1 | 2026-07-02
HR | 20 | Compensation & Benefits | Shirin V. | Risk of overcompensation or undercompensation and percevied inequity | 3D | 1. Periodic benchmark of compensation against industry standards to remain competitive and retain talent 2. Regular audits of payroll and its processes to ensure compliance, equity and alignment with business goals 3. Communication of rationale behind compensation provided to manage expecations and improve transparency 4. Band Mapping of compensation 5. Increment review by Brookfield, exceptions are routed through renumeration committee | 2C | seema | plan 1 | 2026-08-30